## Change Orders
Project | Valencia Distribution Centre — Automated Conveyor and Sortation System (NWL-VAL-2024-07)
Register maintained by | Tidewell Fabrication Ltd (clause 5.5)
CO ref | Date | Title | Value (EUR) | Time (days) | Status | Countersigned by Buyer | Notes
CO-1 | 2024-12-19 | Add second sorter outfeed | 31000 | 7 | approved | Yes — L. Ortega 19/12/2024 | Second sorter outfeed on recirculation line. Reflected in Amendment No. 1.
CO-2 | 2025-01-10 | Upgrade PLC to redundant pair | 17000 | 0 | approved | Yes — L. Ortega 10/01/2025 | Redundant S7-1500 PLC pair. Reflected in Amendment No. 1.
CO-3 | 2025-02-21 | Re-level Bay 3 floor slab (Buyer instruction) | 48000 | 14 | disputed | No | Re-level Bay 3 slab C4–C7 (18 mm over 3 m vs 5 mm tolerance, Levantina LT-2025-0218). Buyer replied 24 Feb 2025: proceed at risk. Not countersigned.
CO-4 | 2025-03-28 | Additional safety fencing | 9500 | 3 | approved | Yes — L. Ortega 28/03/2025 | Additional fencing at outfeed lanes 20–26 at Buyer request.
|  | Total approved | 57500 | 10
|  | Total disputed | 48000 | 14
|  | Original contract price | 1240000
|  | Price after Amendment No. 1 | 1288000

## Milestones
Milestone | Baseline v1 (4 Nov 2024) | Re-baseline v2 (20 Jan 2025) | Actual / forecast | Variance vs v2 (days) | Comment
Design Approval | 2024-12-13 | 2024-12-13 | 2024-12-13 | 0 | Achieved
Delivery | 2025-01-31 | 2025-02-14 | 2025-02-20 | 6 | Last consignment 20 Feb 2025 (sub-supplier)
Mechanical Completion | 2025-03-07 | 2025-03-21 | 2025-03-21 | 0 | Notified 21 Mar 2025 excluding Bay 3 zone C4–C7
Practical Completion | 2025-04-11 | 2025-04-25 | 2025-05-29 | 34 | Forecast per progress report 11; agreement terminated 2 May 2025