# PROJECT KITE — LAUNCH BRIEF

Product: Kite Planner 3.0

Owner: Nadia Rahimi, Product Manager — Larkspur Labs Ltd

Date: 4 July 2025

Status: approved by the leadership team on 7 July 2025

## 1. Why

Kite Planner 2.x is used by 410 customers. The three most requested changes over the last year are a faster dashboard with saved views, single sign-on for enterprise customers, and scheduled report exports. Version 3.0 delivers all three and is the basis for the enterprise tier planned for 2026.

## 2. Goals

Launch on 15 October 2025.

25% of existing customers using 3.0 within 90 days of launch.

Beta net promoter score (NPS) of at least 40 across about 12 beta customers.

Launch within the budget of £120,000 (video, paid media, event, beta incentives, design support, contingency).

## 3. Scope

| Item | Owner | In 3.0? |
| --- | --- | --- |
| New dashboard with saved views | Owen Castillo | Yes |
| Single sign-on (SAML) | Owen Castillo | Yes |
| Scheduled report exports | Priya Sethi | Yes |
| Usage-based billing | Tom Berglund | Stretch goal |
| Launch video, press release, pricing page | Ines Okonkwo | Yes |

## 4. Team and rhythm

Nadia Rahimi (product, overall owner), Owen Castillo (engineering), Ines Okonkwo (marketing), Tom Berglund (finance). Weekly status update every Friday. Kickoff on Tuesday 8 July 2025.

## 5. Milestones

| Milestone | Date |
| --- | --- |
| Kickoff | 8 July 2025 |
| Design review (dashboard) | 14 August 2025 |
| Beta start (about 12 customers) | 1 September 2025 |
| Launch video delivered | 3 October 2025 |
| Go / no-go | 8 October 2025 |
| Launch | 15 October 2025 |

## 6. Risks

Single sign-on is the newest code in the release and has had the least customer exposure; the beta is sized to find problems there. The video and press release depend on an external studio and on the launch date holding.