## Roadmap
Project Kite — roadmap (updated 10 October 2025)
Feature | Owner | Status | Due | Note
New dashboard with saved views | Owen Castillo | Done | 2025-08-29 | Design review 14 Aug: filter bar changes
Single sign-on (SAML) | Owen Castillo | In progress | 2025-10-10 | Multi-role bug found in beta 12 Sep; fix in test
Scheduled report exports | Priya Sethi | Done | 2025-09-05
Usage-based billing | Tom Berglund | Deferred | 2026-01-30 | Moved out of 3.0 scope on 18 Sep
Launch video | Ines Okonkwo | Done | 2025-10-03 | Pixelforge, £21,000
Press release and launch email | Ines Okonkwo | Done | 2025-09-26 | v2 issued 26 Sep
Pricing page update | Ines Okonkwo | In progress | 2025-10-20

## Risks
Risk register
Risk | Likelihood | Impact | Owner | Mitigation
SSO multi-role bug not fixed before go / no-go | Medium | High | Owen Castillo | Fix in test since 6 Oct; fallback is launch without SSO for multi-role tenants
Beta NPS below 40 | Low | Medium | Nadia Rahimi | Survey at 41; follow-up calls with detractors
Video delivery late | Low | Low | Ines Okonkwo | Delivered 3 Oct